## Sheet1
Status | Job # | Job Name | Client Name | Contract Date | As Sold Contract Amount | Approved Change Orders | CO's Added during WIP | Current Contract Amount | Retainage % | Notes | Paula Billings | Total Budgeted Cost (a)
Active | 21108 | Bedford Correctional Facility WWTP | Tam Enterprises | 2022-05-09 | 954500 | 16174 | -13180 |  | 0.05 | Credit to be issued for the project. Vinny to provide more info | 857769 | 776539.2
Active | 23072 | Florida Water Filtration | Tam Enterprises |  | 173000 | 0 | -106575 |  | 0.05 | Credit to be issued for this project. TAM completed remaninging work | 66425 | 53140
Active | 23099 | Delano Hitch | Butler Construction |  | 315000 | 28100 | 0 |  | 0.05 |  | 316100 | 274480
Active | 23108 | WTP Lewisboro | Tam Enterprises |  | 299500 | 5994.45 | -2400 |  | 0.05 |  | 82250 | 243275
Active | 24021 | Twin Towers | Worth Construction |  | 2700000 | 365534.5 |  |  | 0.05 |  | 1099150 | 2268495.53
Active | 24027 | Spencer Field - Croton Harmon | Pierotti |  | 108000 | 0 | 0 |  | 0.05 | Project Completed. No more cost projections | 78600 | 81000
Active | 24030 | Beacon Pump Station | Tam Enterprises |  | 25600 | 1381.53 | -4530.53 |  | 0.05 | What is the status of this project ? Any further billing or closeout ? | 22451 | 16838.25
Active | 24047 | Brewster H.S | Pierotti |  | 65785 |  |  |  | 0.05 | Issue Credit change Order and Retainage Invoice. | 60135 | 52628
Active | 24053 | BOCES - Orange & Ulster (ArdenHill) | Key Construction |  | 269000 | 19008 |  |  | 0.05 | Change Order confimed vias email. Need full execution | 33625 | 230406.4
Active | 24059 | Valley Cottage - Fisherman | ADP Group |  | 148000 | -800 |  |  | 0.05 |  | 0 | 106309.73
Active | 24062 | Katonah - John Jay MS | Grace Contracting |  | 84320 | 551.21 |  |  | 0.05 | Do we need to go back to finish or can we fully bill it out ? Invoice 1 was shortpaid, John has reached out to get more information on this. | 27849.6316 | 67896.968
Active | 24073 | Rockland Pomona | ADP Group |  | 68100 |  | -22080 |  | 0.05 | A credit invoice needs to be issed and the retainage for it to be billed. | 46020 | 36816
Active | 24130 | Schlathaus Stage | Barone Construction Group | 2025-01-29 | 152000 | 0 | 0 |  | 0.05 | Project Completed. No more cost projections | 0 | 115747.288
Active | 24120 | Church Street Elementary School | Pierotti | 2025-02-10 | 68500 | 0 |  |  | 0.1 |  | 0 | 51375
Active | 24058 | Kerhonkson Wastewater Treatment Facility | J Squared Construction |  | 418200 | 34750 |  |  | 0.05 |  | 0 | 332494.074
Active | 24119 | Mamaroneck Elementary | Pierotti | 2025-03-04 | 15500 | 0 |  |  | 0.1 |  | 0 | 11625
Active | 24127 | Ulster County BOCES Axelrod main building alterations | Key Construction |  | 557500 | -1925 | 17981.48 |  | 0.05 | 1. Key Construction - 24127; Amount : $21642.18 (Invoice Date : 12/31/2025 | 0 | 404776
Active | 24126 | Stony Point Headworks | Gallo Construction | 2025-02-11 | 1065000 | 0 | 0 |  | 0.05 |  | 0 | 892591
Active | 24125 | Greenwood Lake School | Butler Construction |  | 55000 | 0 | -1000 |  | 0.1 |  | 0 | 40500
Active | 25032 | Roger Ludlowe | Derosa Sports | 2025-03-18 | 168500 | 0 | 0 |  | 0 | Project Completed. No more cost projections | 0 | 124012.656
Active | 24121 | Patterson EMS Building | Nurzia Construction | 2025-02-20 | 154000 | 0 | 0 |  | 0.05 |  | 0 | 115500
Active | 25019 | Nanuet Union Free School District | Mt Olympus | 2025-05-14 | 65500 | 750 | 0 |  | 0 |  | 0 | 49687.5
Active | 25034 | WL Morse Elementry School | APS | 2025-04-10 | 708000 | 8680 | 0 |  | 0.05 |  | 0 | 502980.46
Active | 25005 | Middletown -ECST Cold Storage | Malum Excavating | 2025-04-25 | 86000 | 19950 | 0 |  | 0.05 | Project Completed. No more cost projections | 0 | 79462.5
Active | 24084 | Cromline Creek | TAM | 2025-05-05 | 175600 | 3500 | -2085.33 |  | 0.05 |  | 0 | 132761.0025
Active | 25050 | New Roc HS Stairs | GL Group | 2025-05-06 | 260000 | 32000 | -57150 |  | 0.05 |  | 0 | 176137.5
Active | 25021 | Ulster County Operations Center | Andron Construction | 2025-06-17 | 1334000 | 70000 | 0 |  | 0.05 | We will need to update the Invoice AIA Inv#4 Operations Center. The last description of Concrete Infill at Duck Banks amounting to $ 6,009.36 have to be moved from previous application to this period. | 0 | 1017584.18
Active | 25037 | Edgemont UFSD | Pierotti | 2025-05-21 | 345000 | 0 | 0 |  | 0.05 |  | 0 | 305894
Active | 25024 | Ardon Hill - Gym Add | Andron Construction | 2025-06-24 | 499000 | 4359.98 | 0 |  | 0.05 |  | 0 | 422058.3
Active | 24124 | Maybrook Solar Equipment Pads and Bollards | Butler Construction | 2025-07-25 | 43000 | 0 | -3600 |  | 0.05 |  | 0 | 29550
Active | 25057 | Memorial Park Spray Pad | Abott and Price |  | 61833.6 | 0 | -1937.5 |  | 0.05 |  | 0 | 44922.075
Active | 25078 | Ceasars Lane WWTP Phase 1 | Barone Construction Group |  | 30000 |  |  |  | 0 |  |  | 22500
Active | 24085 | Rockland Screening Building Addition | Tomar Construction |  | 260000 | 18450 |  |  | 0.075 |  |  | 208837.5
Active | 25073 | Route 118 | Abott and Price |  | 91188 |  |  |  | 0.05 |  |  | 68391
Active | 24079 | Tuxedo Farm Route 17 Culvert | Brennan Construction |  | 179241 | 0 | 0 |  | 0.05 |  | 0 | 134430.75
Active | 25015 | South St Parking Garage | Malum Exacavation |  | 887000 |  |  |  | 0.05 |  |  | 665250
Active | 25080 | Wisner Ave Sidewalk | Malum |  | 7200 |  |  |  | 0
Closed | 23037 | Green Haven | Nurzia |  | 186586.6 |  |  |  | 0.05 | We just collected the retainingae. Have no information on this project | 186586.6
Closed | 24003 | Warawrsing | Tam |  | 44000 | -1700 |  |  | 0.05 | Retainage Collected. Bill to confirm. | 42300
Closed | 23038 | Crawford Pine Bush Well Site - GC Contract | Tam |  | 44053.2 |  |  |  | 0.05 | Retainage Collected. Bill to confirm. | 44053.2
Closed | 24086 | Veolia Monsey Monople | Innovative Excavating |  | 50000 |  |  |  | 0 | All nivoices has been collected and hence the project is inactive. | 50000
Closed | 20161 | Town of Wawarsing- Water District WTP | TAM |  | 344000 |  |  |  | 0.05 |  | 344000
Closed | 23015 | JFK Elementary | Pierotti |  | 207000 |  |  |  | 0.05 |  | 207000
Retainage | 23082 | Beacon School | Key Construction |  | 67000 | 4800 |  |  | 0.05 | We have a retainingage of 3590 to be collected. Bill to provide recommendation | 71800
Retainage | 23088 | Ellenville | Empire Core |  | 32500 |  |  |  | 0.05 | Contractor went under | 32500
Retainage | 23120 | Ramapo HS | Pierotti |  | 43353.85 | 5462.35 |  |  | 0.05 | We have a retainage of 2440.810 to be collected. Bill to provide recommendation | 48816.2
Retainage | 23121 | Valve Vault Poughkeepsie | Pierotti |  | 32109.5 |  |  |  | 0.05 | John to confirm if there is a retaininge pending on this project to be collected. Update A/R sheet once we have insights on this retainage | 32109.5
Retainage | 24038 | Beacon School - Change Order | Key Construction |  | 20000 |  |  |  | 0.05 | John to confirm if retaiinage is pending on this project. Update A/R sheet once we have insights on this retainage | 20000
Retainage | 24068 | Valley Central | Butler Construction |  | 53000 |  |  |  | 0.05 | We have a retainage of 2,650.00 to be collected. Bill to provide recommendation | 53000
Retainage | 21062 | SUNY Backflow & Pump Station | All State Construction |  | 166860.6 |  |  |  | 0.05 | We have a retainage of 8343.03 to be collected. Bill to provide recommendation | 166860.6
To Begin | 25066 | Peekskill Admin Building | Grace Contracting |  | 0 |  |  |  | 0.05 |  |  | 0
Active | 25059 | Tapanzee HS Auditorium | BLH |  | 40000 |  |  |  | 0.05 |  |  | 30000
To Begin | 25067 | Rockland Green